## survey
Project Plan | Project Start Date | Project End Date
| 2018-01-22 | 2018-04-28
Survey
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Customer Meeting | Done | 2018-01-22 | 2018-02-06 | 16
Requirements | Done | 2018-02-05 | 2018-02-09 | 5
CSS/HTML Format (Main Page Survey) | Done | 2018-02-15 | 2018-02-18 | 4
Mind Map | Done | 2018-02-15 | 2018-02-18 | 4
Database Design Survey | Working on it | 2018-02-20 | 2018-02-23 | 4
Integrate Database onto Surveys | Working on it | 2018-02-21 | 2018-03-05 | 13
Code on Pretest Page Adding buttons | Working on it | 2018-02-21 | 2018-03-05 | 13
Code on Post Test Page Adding buttons |  | 2018-03-05 | 2018-03-12 | 8
Report CSV Files (Individual) |  | 2018-03-10 | 2018-03-11 | 2
Report CSV Files (Composite) |  | 2018-03-10 | 2018-03-11 | 2
Test Survey
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Verify the workflow of the system |  | 2018-03-10 | 2018-03-13 | 4
Verify there are no Dead Page or invalid indirects
Verify Inputs on negative test
Verify the data Integrity
User Interface consist components
Ensure missing answers on page have highlights
Test authentications
Reports are working
Split questions onto multiple pages for both Test |  | 2018-03-05 | 2018-03-12 | 8
Evaluation
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Evaluation page HTML and CSS style | Working on it | 2018-02-21 | 2018-03-08 | 16
Design User Interface | Working on it | 2018-02-21 | 2018-03-06 | 14
Database Design for Evaluation |  | 2018-03-05 | 2018-03-13 | 9
Database Securities for Evaluation |  | 2018-03-06 | 2018-03-12 | 7
Database Evaluation Integrated with Evaluation Survey |  | 2018-03-10 | 2018-03-11 | 2
Reports
Graph
Evaluation Test
Name | Phase | How long will this take - Start | How long will this take - End
Verify the workflow of the system
Verify there are no Dead Page or invalid indirects
Verify Inputs on negative test
Verify the data Integrity
User Interface consist components
Test authentications
Ensure no SQL injections on Database
Reports are working